MVP DELIVERY BACKLOG

SteadFast Development Backlog

Ordered, security-aware implementation plan from foundation through pilot

Document owner: SteadFast Product and Engineering

Status: Ordered MVP implementation backlog

Version: 0.1

Date: 16 July 2026

# 1. Delivery objective

Build the smallest secure vertical slice first: an invited agent signs in, creates a valid residential sale or long-term rental listing, submits it, authorized brokerage personnel approve it, and the approved listing appears in public search and on the correct agent and brokerage websites.

# 2. Definition of ready

A backlog item is ready when it has:

clear user outcome and owner;

linked product, permission, workflow and data rules;

acceptance and abuse/security criteria;

design state for user-facing work;

migration/API impact;

dependencies and test approach;

no unresolved business decision that changes the implementation.

# 3. Definition of done

Acceptance criteria pass.

Server authorization and applicable RLS are implemented and negatively tested.

Runtime validation, errors, loading, empty and accessibility states exist.

Audit and notification events are correct.

Unit, database, integration and E2E tests pass.

Preview reviewed on desktop and mobile.

Security/privacy checklist and threat model updated where needed.

Migration is reversible/compatible and documentation is current.

No critical/high unresolved defect.

# 4. Milestone map

| Milestone | Outcome | Depends on |
| --- | --- | --- |
| M0 Foundation | Reproducible secure delivery pipeline | Existing prototype |
| M1 Identity and brokerage | Real users and tenant boundaries | M0 |
| M2 Listing draft | Agent can create a complete private draft | M1 |
| M3 Approval and publication | Brokerage-approved listing reaches public projection | M2 |
| M4 Public discovery | Visitors search, map and inquire | M3 |
| M5 Websites and sharing | Agent/broker sites and display permissions | M4 |
| M6 Billing and operations | Subscriptions and support controls | M1-M5 |
| M7 Integrations | Approved external channel framework | M3, contracts |
| M8 Pilot hardening | Tested, recoverable and legally ready pilot | All P0 |

# 5. M0 — Foundation and delivery

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| FND-001 | P0 | Protect main branch and define pull-request template | Direct pushes blocked; review and test evidence required |
| FND-002 | P0 | Add CI for install, lint, typecheck, test and build | Required checks run on every pull request |
| FND-003 | P0 | Create preview/staging/production environment contract | Variables documented and isolated by scope |
| FND-004 | P0 | Add secret scanning and dependency alerts | Test secret fails CI; lockfile scanning active |
| FND-005 | P0 | Establish Supabase migration structure | Fresh database builds from zero deterministically |
| FND-006 | P0 | Add test framework and seeded two-broker fixtures | Role accounts and cross-tenant data available in tests |
| FND-007 | P0 | Add request ID, safe error envelope and structured logging | No secret/session leakage; request trace available |
| FND-008 | P0 | Add monitoring and uptime provider adapters | Test error and outage alert reach owner |
| FND-009 | P1 | Feature-flag service | Flag changes are scoped and audited |
| FND-010 | P1 | Architecture decision record template | Material technical decisions are discoverable |

# 6. M1 — Identity, roles and brokerage

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| IAM-001 | P0 | People, brokerage, membership, role and grant migrations | Constraints match approved database design |
| IAM-002 | P0 | RLS and explicit grants for identity domain | Cross-broker access fails for every role |
| IAM-003 | P0 | Supabase SSR session validation and DAL | Protected routes/actions verify active database state |
| IAM-004 | P0 | Consumer registration, sign-in/out and recovery | Secure sessions and safe redirects tested |
| IAM-005 | P0 | Brokerage invitation and application flow | Invitation is bound, expiring and single-use |
| IAM-006 | P0 | Broker/staff approve or deny agent | Decision is scoped and audited |
| IAM-007 | P0 | Staff capability management | Broker grants/revokes explicit capabilities |
| IAM-008 | P0 | One active brokerage membership enforcement | Second active membership is rejected atomically |
| IAM-009 | P0 | Agent departure service | Membership ends and represented listings unpublish |
| IAM-010 | P0 | Capability-aware navigation and access-denied states | UI matches permission matrix; server remains authoritative |
| IAM-011 | P0 | MFA for operations/admin; policy for broker/staff | Elevated login requires approved factor |
| IAM-012 | P1 | Active-session view and revoke | User can terminate other sessions |

# 7. M2 — Listing draft and media

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| LST-001 | P0 | Property, address, listing, assignment and version migrations | Tenant and representative constraints enforced |
| LST-002 | P0 | RLS for listing domain | Agent/staff/broker matrix passes positive/negative tests |
| LST-003 | P0 | Create-listing wizard shell and autosave | Seven steps save/recover without data loss |
| LST-004 | P0 | Sale and long-term rental validation schemas | Required/bounded fields validated server-side |
| LST-005 | P0 | Address normalization and map confirmation adapter | Failed geocode requires correction |
| LST-006 | P0 | Private upload authorization | User can upload only into permitted brokerage/listing path |
| LST-007 | P0 | Media validation and derivative worker | Type mismatch, oversize and invalid images rejected |
| LST-008 | P0 | Draft preview and completeness check | Public-like preview shows validation gaps |
| LST-009 | P0 | Draft history and optimistic concurrency | Conflicting edit returns a recoverable 409 |
| LST-010 | P1 | Duplicate property/listing warning | Likely duplicates surfaced without blocking valid work |

# 8. M3 — Approval and publication

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| APR-001 | P0 | Review, decision, audit and outbox migrations | Immutable relationships and timestamps enforced |
| APR-002 | P0 | Submit-listing transaction | Submitted version freezes and queue item appears |
| APR-003 | P0 | Approval queue | Authorized reviewer filters and opens scoped work |
| APR-004 | P0 | Version comparison UI | Every changed/removed material field is visible |
| APR-005 | P0 | Return/reject with reason | Agent receives reason and preserved history |
| APR-006 | P0 | Atomic approve-and-publish function | Eligibility rechecked; pointer/snapshot/audit/outbox commit together |
| APR-007 | P0 | Self-approval behavior | Allowed staff/broker can approve; event is explicitly marked |
| APR-008 | P0 | Material-change workflow | Approved public version remains until new approval |
| APR-009 | P0 | Removal and sold/rented approval | Public state changes only after decision |
| APR-010 | P0 | Unassigned listing queue/reassignment | Publication requires new active representative and approval |
| APR-011 | P0 | Snapshot reconciliation job | Drift is detected and repair is audited |

# 9. M4 — Public discovery and inquiry

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| PUB-001 | P0 | Sanitized public listing projection | Private fields are impossible to select anonymously |
| PUB-002 | P0 | Public search API | Bounded filters, cursor pagination and cache policy |
| PUB-003 | P0 | Search list and responsive filters | URL-preserved filters work without registration |
| PUB-004 | P0 | Map bounds and clustering | Area clusters at wide zoom; listings at close zoom |
| PUB-005 | P0 | Property detail | Approved data, media, map and contact cards render |
| PUB-006 | P0 | Inquiry storage and consent record | Minimal data, selected contact and source are recorded |
| PUB-007 | P0 | Inquiry routing/outbox | Primary and secondary notices are correct and idempotent |
| PUB-008 | P0 | Anonymous abuse controls | Inquiry/search limits resist automation without normal-user failure |
| PUB-009 | P0 | SEO canonical, sitemap and noindex rules | Only eligible public URLs are indexed |
| PUB-010 | P1 | Registered consumer inquiry history | Consumer sees own submitted inquiries only |
| PUB-011 | P2 | Favorites and saved searches | Explicitly deferred from initial vertical slice |

# 10. M5 — Websites, sharing and notifications

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| WEB-001 | P0 | Site/domain migrations and hostname resolver | Only verified hostnames select a site |
| WEB-002 | P0 | Agent public website | Owned plus accepted shares display correctly |
| WEB-003 | P0 | Brokerage public website | All eligible brokerage-owned listings display |
| WEB-004 | P0 | Share grant/accept/revoke/remove workflow | Recipient cannot edit; history preserved |
| WEB-005 | P0 | Dual-agent property contact | Owner/display agent shown and consumer chooses |
| WEB-006 | P0 | Share change notifications | Approved listing changes notify active display agents |
| WEB-007 | P0 | Recipient-removal notification | Owner receives notice and site removes listing |
| WEB-008 | P0 | Agent departure website behavior | Account/site remains; former brokerage inventory disappears |
| WEB-009 | P1 | Basic site branding/profile controls | Safe colors/logo/profile with preview |
| WEB-010 | P1 | Wildcard subdomain deployment | DNS, TLS, cookies and hostname tests pass |
| NTF-001 | P0 | Notification preferences and inbox | Required operational notices cannot be disabled improperly |
| NTF-002 | P0 | Outbox worker retry/dead-letter | Delivery is idempotent and observable |

# 11. M6 — Billing, operations and administration

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| BIL-001 | P0 | Plan, subscription, seat, invoice and payment migrations | JMD/provider IDs/status history represented |
| BIL-002 | P0 | Payment provider sandbox integration | SteadFast never stores raw card data |
| BIL-003 | P0 | Signed idempotent webhook processing | Forged/replayed events rejected |
| BIL-004 | P0 | Entitlement service | Browser cannot grant subscription capability |
| BIL-005 | P0 | One-person/combined-capability billing | Agent-plus-staff/broker pays once under approved plan rules |
| BIL-006 | P1 | Invoice and payment history UI | User and operations see permitted records |
| OPS-001 | P0 | Operations customer context | Scoped support view with reason and audit |
| OPS-002 | P0 | System flag workflow | Operations can notify brokerage but not control content |
| OPS-003 | P0 | Delivery and outbox health | Failures can be retried within capability |
| ADM-001 | P0 | Admin access and audit | MFA, reason and immutable event for elevated actions |
| ADM-002 | P1 | Plan/configuration management | Changes versioned, validated and reversible |

# 12. M7 — External integrations

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| INT-001 | P1 | Canonical approved export model | Contains only authorized approved fields |
| INT-002 | P1 | Channel credential vault/adapter interface | Credentials isolated and rotatable |
| INT-003 | P1 | Distribution queue and delivery attempts | Idempotent retries and dead-letter state |
| INT-004 | P1 | Field/value mapping and validation | Provider-specific errors are actionable |
| INT-005 | P1 | Acknowledgement and reconciliation | External ID/status recorded and drift surfaced |
| INT-006 | P1 | Channel entitlement and brokerage consent | No export without contract, plan and authorization |
| INT-007 | P1 | First contracted channel certification | Written spec and acceptance evidence attached |
| INT-008 | P2 | Additional country/channel adapters | After Jamaica pilot and country/legal analysis |

No channel should be named “live” until commercial permission, current specification, credentials, certification and monitoring exist.

# 13. M8 — Pilot hardening and launch

| ID | Pri | Item | Acceptance |
| --- | --- | --- | --- |
| PIL-001 | P0 | Full role and cross-tenant test suite | All matrix cases pass |
| PIL-002 | P0 | Accessibility/manual usability study | Critical novice/accessibility issues resolved |
| PIL-003 | P0 | Performance/load test | Pilot targets and provider quotas validated |
| PIL-004 | P0 | Backup tier and restore drill | Approved RPO/RTO met with recorded evidence |
| PIL-005 | P0 | Incident runbooks and contact rota | Tabletop completes for major scenarios |
| PIL-006 | P0 | Privacy/data inventory and retention configuration | Every personal-data class has owner/purpose/retention |
| PIL-007 | P0 | Counsel-approved legal pack | Terms/notices/agreements approved and published |
| PIL-008 | P0 | Pilot brokerage onboarding and support process | Responsibilities, contacts and escalation tested |
| PIL-009 | P0 | Independent security assessment | No unresolved critical/high finding |
| PIL-010 | P0 | Production readiness review | Named owners approve product, security, legal and operations gates |
| PIL-011 | P1 | Pilot metrics dashboard | Adoption, approval time, inquiry and reliability visible |

# 14. Recommended sprint sequence

FND-001 through FND-008.

IAM-001 through IAM-010.

LST-001 through LST-009.

APR-001 through APR-011.

PUB-001 through PUB-009.

WEB-001 through WEB-008 and NTF-001/002.

Billing/operations P0.

Pilot hardening P0.

First contracted integration only after its external dependency is ready.

Keep each sprint vertically demonstrable. Avoid building a full set of screens on mock data before the authorization, data and workflow path exists.

# 15. Backlog risks and dependencies

| Risk/dependency | Effect | Response |
| --- | --- | --- |
| External feed terms/spec unavailable | Integration cannot be estimated/certified | Build adapter framework; keep channel disabled |
| Free hosting/database limits | Pilot reliability/backups may be insufficient | Measure early; approve paid tier before live data |
| Legal entity/privacy decisions missing | Legal pack cannot be finalized | Counsel checklist and launch blocker |
| Map licence/address quality | Search/location experience may vary | Provider spike and Jamaica address test set |
| Payment provider/currency choice | Billing implementation delayed | Provider decision before M6 |
| Complex RLS | Security/performance defects | Policy patterns, indexes and automated matrix |
| Novice usability | Adoption failure | Prototype and test vertical slice early |

# 16. Explicitly deferred

Vacation rentals.

Transaction/closing management, commissions and trust accounting.

Native iOS/Android applications.

Public partner API and third-party developer portal.

Multi-broker membership for one agent.

Automated AI-generated listing content without separate policy.

Belize or other country rollout before Jamaica pilot evidence and jurisdiction review.

Favorites/saved searches if schedule threatens P0 professional workflow.